## Cover Page
STATE BUSINESS-ENABLING REFORM ACTION PLANS (BERAP)
State: | PLATEAU
Reporting period: |  | FY 2023
SABER Focal Person: |  | EZEKIEL GOMOS
List of contributing entities: |  |  | PS-OSIC, Min. of Tourism, Min. of Commerce & Industry, Plateau State Internal Rev. Service, Plateau State Small and Medium Enterprsie Dev, Agency, Min. of Justice, Ministry of Works, Ministry of Agriculture, MLS&TP, Jos Metropolitan Dev. Board, GOVERNOR'S OFFICE
URL Link to the published BERAP |  |  | www.plateaustate.gov.ng
Is this plan approved by the State Executive Council (SEC) |  |  |  |  | YES
If this was approved by SEC, please state date: |  |  |  | 2023-01-19

## BERAP
BUSINESS-ENABLING REFORM ACTION PLAN (BERAP)
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Responsible MDA | Contributing MDAs | Budget (Naira) | Planned Start Date | Planned End Date
1 | Enactment of the Plateau State Micro, Small and Medium Enterprises (MSME) Policy | This reform area will further drive the development and growth of MSMEs in Plateau State for income generation and job creation | A. Development of policy implementation manual | Private Sector, Business Member Organizations, MSMEs and Potential investors. | Plateau State Micro -Finance Development Agency (PLASMIDA) | Plateau State Ministry of Commerce and Industry, Plateau Investment and Property Development Company (PIPC) Ltd, Small and Medium Enterprise Development Agency of Nigeria (SMEDAN) , Industrial Training Fund (ITF), Standard Organization of Nigeria (SON),National Agengy for Food and Drug Administration and Control (NAFDAC), Corporate Affairs Commission (CAC), Project Monitoring and Result Delivery Office (PMRDO), Ministry of Lands Survey and Town Planning, Ministry of Agriculture and Rural Development, Jos Metropolitan Development Board (JMDB), Nigerian Expo Promotion Council (NEPC), Plateau State One Stop Investment Centre, Ministry of Women Affairs, Office of the Governor |  | 5th January 2022 | 31st March, 2023
Target Objective: It helps to define goals, conduct research, map out risks, schedule milestones, assign responsibilities/tasks and allocate resources
|  |  | B. Produce and distribute policy and implementation manual to relevant Stakeholder | Target Objective: Produce 500 copies of the policy implementation manual and distribute to the relevant Stakeholders | Plateau State Micro -Finance Development Agency (PLASMIDA)
|  |  | C. Undertake advocacy on policy and the implementation Strategies | Target Objective: Launch a publicity campaign leveraging a range of communication platforms including radio, television, social media, mobile phones, Internet, amongst others, to raise awareness on the policy and emerging programmes from the implementation of policy priorities by 50% | Plateau State Micro -Finance Development Agency (PLASMIDA)
|  |  | D. Implement policy and track performance | Target Objective: To ensure identified risks are mitigated, identified blockages are fixed and deadlines are met | Plateau State Micro -Finance Development Agency (PLASMIDA)
|  |  | E. Collate Statistics and data on implementation | Target Objective: Towards measuring the effectiveness of the reform strategy | PLAMIDA
|  |  | F. Monitor and evaluate policy implementation periodically | Target Objective: Review and assessment of the process, effeiciency and effects of the policy development and implementation to inform policy adaptation and reform. Secondly, Apply evaluation principles and methods to examine the context, implementation or impact of the policy in order to understand its merit, worth and utility | PLASMIDA, Plateau State MSME Council, Office of the Governor
2 | Land, Property Titling and Use | Administrative reforms and streamlining of land registration procedures | A. More sensitization on the Land Use charge to simplify access to Land for business | All Private Sector Players, Business Owners, potential investors and MSMEs | Plateau State Ministry of Lands, Survey and Town Planning | Plateau State Ministry of Lands, Survey and Town Planning, Jos Metropolitan Development Agency (JMDB), Plateau State Ministry of Urban and Physical Planning, Plateau State One Stop Investment Centre, Plateau State Small and Medium Development Agency (PLASMIDA), Plateau Investment and Property Development Company (PIPC) Ltd, Ministry of Justice |  | 14th July, 2021 | 31st December, 2023
|  |  |  | Target Objective: Increase awareness by 70% on the Land use charge for businesses | Plateau State Ministry of Justice
|  |  | B. Ease the criteria and procedures for registering land for business | Target Objective: Reduce the land registration processes and procedures for businesses to five steps | Plateau State Ministry of Lands, Survey and Town Planning
|  |  | B.1. Design simpler and more transparent procedures for land transactions and Titling | Target Objective: The guidelines help make land deals more transparent by urging governments to conduct impact assessments of proposed investments in land to determine their impact on local people and land rights. | Plateau State Ministry of Lands, Survey and Town Planning
|  |  | C. Reduce the time/days taken for land and property titling | Target Objective: Improve service speeds, and ensure expedited urgent applications processed within 30 working days | Plateau State Ministry of Lands, Survey and Town Planning
Plateau State Ministry of Lands, Survey and Town Planning
|  |  | D. Sustain the cost of acquistion process of land/property by 50% | Target Objective: Provide sustainable solution that will facilitate and increase land ownership transaction and environment-friendly workspace by 80% | Plateau State Ministry of Lands, Survey and Town Planning
Plateau State Ministry of Lands, Survey and Town Planning
Plateau State Ministry of Lands, Survey and Town Planning
3 | Reducing the number of steps and time for processing building permit approval | Improve transparency, efficiency and facilitate access to regulations | A. Identify the relevant MDAs involved in the inspection process | All Private Sector Players, Business Owners, potential investors and MSMEs. Target Objective: To ensure interactions within the reform system to produce substantail impact by 80% | Jos Metropolitan Development Board (JMDB) | Jos Metropolitan Development Board, Plateau State Lands, Survey and Town Planning (Office of the Surveyor General) |  | 9th November, 2022 | 16 February, 2023
|  |  | A.1. Develop a schedule to jointly inspect a site and identify lead agency | Target Objective: To ensure that project activities go forward as planned and are according to requirements, standard and regulations | Jos Metropolitan Development Board (JMDB)
|  |  | B. Communicate to the revised procedures to the personnel | Target Objective: This is essential in order to avoid costly mistakes and errors | Jos Metropolitan Development Board (JMDB)
|  |  | B.1. Communicate to relevant stakeholders within the sector | Target Objective: To gain greater understanding of the set objectives and adapt to deliver on the project mandate | Jos Metropolitan Development Board (JMDB)
|  |  | B.2. Automate the process of obtaining permit | Target Objective: Cost reduction, increase productivitiy and availability by 50% | Jos Metropolitan Development Board (JMDB)
|  |  | C. Implement and track performance | Target Objective: Mitigate risk and meet deadlines | Jos Metropolitan Development Board (JMDB)
|  |  | C.1. Collate Statistics and data on implementation | Target Objective: Towards measuring the effectiveness of the reform strategy | Jos Metropolitan Development Board (JMDB)
4 | Comprehensive Reform of State Tax Administration | Harmonization of the Plateau State tax system to reduce regulatory burden on MSMEs and the private sector | A. Eliminate tax raids and multiple tolls on MSMEs | Private Sector, MSMEs and potential investors. Target Objective: The harmonization of the tax laws will reduce tax raid and multiple tolls on MSME by 60% | Plateau State Board of Internal Revenue Service (PSIRS) and Local Government Council | Plateau State Board of Internal Revenue Service (PSIRS), Local Government Council, Federal Inland Revenue Services, Office of the Governor |  | 21st November, 2021 | 29th December, 2023
|  |  | B. Rationalized tax administration to reduce overlapping between tiers of government | Target Objective: This will strengthening tax capacity towards improving governance and accountability | Plateau State Board of Internal Revenue Service (PSIRS)
|  |  | C. Document and disseminate whole tax obligations of MSMEs according to sectors and to all tiers of government | Target Objective: To increase the process of filing and paying taxes on a timely basis by 70% | Plateau State Board of Internal Revenue Service (PSIRS)
5 | A bill for a law to establish the Co-operative societies Commission | Easing the process for business and cooperative registration and formalization | A. The Cooperative Agency Bill when passed into law will enhance the process for registering cooperative societies and fast-track the growth of cooperatives as engine room of grassroots development. | MSMEs, Private Sectors. Target Objective: Enhance registration of cooperative societies by 30% | Plateau State House of Assembly | Plateau State Ministry of Justice, Ministry of Commerce, Plateau State House of Assembly, PSIRS |  | 31st March, 2023 | 31st December, 2023
|  |  | B. Create awareness and Compliance to the Cooperative laws by MSMEs | Target Objective: Increase awareness and compliance by 60%
6 | Contract Enforcement and Dispute Resolution | This reform is aimed at reducing the cost and process of settling commercial disputes especially by MSMEs in Plateau State | A. Strengthen the exisiting Alternative Dispute Resolution mechanism (Mediation and Reconciliation) | MSMEs, Private Sectors and Potential Investors. Target Objective: To increase rapidity, confidentiality and flexbility in resolving commerial disputes by 20% | Plateau State Ministry of Justice | Plateau State Ministry of Justice, Plateau State Judiciary, Plateau State House of Assembly |  | 7th November, 2022 | 16th September, 2023
|  |  | A.1. Establish more Alternative Dispute Resolution Centre across the State | Target Objective: 40% Increase in dispute settlements in a more cost-effective manner | Plateau State Ministry of Justice
|  |  | A.2. Ensure the speedy completion of the Plateau State Multi-door court house and make it fully funtional | Target Objective: To facilitate the speedy implemention of the Alternative Dispute Resolution strategies to business conflicts
|  |  | B. Sensitize and conduct publicity campaigns to MSMEs on the workings of the Alternative Dispute Resolution and to utilize them | Target Objective: Increase awareness Alternative Disputee Resolution Mechanism by 40% | Plateau State Ministry of Justice
|  |  | C. Establish small claims courts across the State | Target Objective: To urgently address speed of adjudication, particularly on financial claims, and to reduce cases from the dockets of the high courts over a simple commecial dispute by 40% | Plateau State Ministry of Justice
7 | Human Resource Development | Improve the required skills to be more responsives to the industry needs | A. Design specialized courses on skills development for youths, women and People With Disabilities (PWDs) | MSMEs, Enterprenuers, Business Operators. Target Objective: To aviod by 20% mismatch between skills training and labour markets requirements | Plateau State Ministry of Education | Plateau State Ministry of Education, Business Service Providers (BSPs), PLASMIDA, PIPC Ltd, ITF, NDE, Development Partners |  | 21st February, 2023 | 31st December, 2023
|  |  | B. Establish more vocational centres across the State and Stengthen exisitng centres | Target Objective: 20% Increase in skills development across the State | Plateau State Ministry of Education
|  |  | C. Assist MSMEs to conduct regular skills audit and fill gaps | Target Objective: To systematically assess a research on skills and knowledge gaps, and provide evidence of evidence of exisitng or developing competence by 20% | PLASMIDA
|  |  | D. Established institutional mechanisms to train, accredit and certify MSMEs, entrepreneurs and managers | Target Objective: Increase provision of guidance, allow for routines to develop and ultimately reduce the uncertainity of social interaction by 10% | PLASMIDA
8 | Technology , Research and Development | This reform is expected to support the development of our digital economy and facilitate digital literacy and accelerate broadband penetration across the state. It is also expected to attract more investment in TELCOS and create job opportunities | A. Facilitate access of MSMEs to productive enhancing technology innovations, research and development result | Private Sector, MSMEs: Target Objective: Promote of peaceful and inclusive societies for sustainble development | Plateau State Information and Communication Technology Development Agency (PITCDA) | Plateau State Information and Communication Technology Development Agency (PITCDA), Plateau State Small and Medium Development Agency (PLASMIDA), Small and Medium Enterprise Development Angency of Nigeria (SMEDAN), National INformation Technology Development Agency (NITDA), Private Sector Technological Providers |  | 3rd March, 2023 | 31st December, 2023
|  |  | A.1. Provide private Sector Technology Developers and Researchers with Competitive special grants for research and innovation to develop technology products for MSMEs | Target Objective: To train 200 technology developers on hands-on skills needed for construction, maintenance, and repair of IT equipment and gadgets and provide special grants | PLASMIDA
|  |  | B. Enhance synergy between the various State and Federal MDAs that promotes technology and innovations for MSMEs | Target Objective: To promote the fulfilment of the goal of 30% digital literacy and skills at State level | Plateau State Small and Medium Development Agency (PLASMIDA)
|  |  | B.1. Establish coordination programmes to link the support MDAs | Target Objective: Engage the stakeholders at the state and local government levels to support the goal of 30% digital literacy level | Plateau State Small and Medium Development Agency (PLASMIDA)
|  |  | C. Improve awareness and application of technological products and innovation | Target Objective: To enable a progressive increase in the contribution of digital technologies to the State economy | Plateau State Information and Communication Technology Development Agency(PITCDA)
|  |  | C.1. Organized regular technological fairs and exhibitions to expose technological products and innovations | Target Objective: To inspire young people to develop interest in digital technologies and innovation | Plateau State Information and Communication Technology Development Agency(PITCDA)
9 | Improving the investment climate and investment facilitation services for private sector investment | A Bill for a Law to establish Investment Promotion Agency in Plateau State to attract foreign direct investments and strengthen local businesses | The IPA bill has been developed and sent to the Plateau State House of Assembly. | Investors, MSMEs, private sector. Target Objective: Reduce the cost of doing business, and drive job creation and income growth | Ministry of Justice | Plateau State Ministry of Commerce and Industry, Ministry of Justice, Plateau State One Stop Investment Centre (PS-OSIC), PIPC, Plateau State House of Assembly |  | 6th December 2022 | 31st March,2023
10 | Launch of Plateau State Agricultural Policy | The policy is developed to drive the growth of the agriculture sector with attention on key contemporary issues such as poverty, climate change, gender, PLWDs, inputs support and data | A. Development of policy implementation matrix with focus on the SDG elements | MSMEs, Farmers, Private Sector: Target Objective: To increase adoption of the Sustainable Develoment Goals (SDG) in Plateau State; and improvement of the efficiency & effectiveness of government services | Plateau State Ministry of Agriculture and Rural Development | Plateau State Ministry of Agriculture and Rural Development, Ministry of Environment, Federal Ministry of Agriculture and Rural Development (FMAD), Local Government Areas |  | 10th January, 2023 | 31st December, 2023
|  |  | B. Produce and and distribute policy and implementation manual to relevant Stakeholder | Target Objective: Produce copies of the policy implementation manual and distribute to the relevant Stakeholders | Plateau State Ministry of Agriculture and Rural Development
|  |  | C. Undertake advocacy on policy and the implementation Strategies | Target Objective: To enable a progressive increase in the contribution of policy to the State economy | Plateau State Ministry of Agriculture and Rural Development
|  |  | D. Implement policy with focus in key areas that meets SDGs Objectives | Target Objective: To strengthen SDGs objectives through evidence based practical approach | Plateau State Ministry of Agriculture and Rural Development
|  |  | E. Monitor and Evaluate policy implementation periodically | Target Objective: To develop evaluation tools and assess the impacts of smart project | Plateau State Ministry of Agriculture and Rural Development
11 | Mainstreaming Gender and Vulnerability in the distribution of State Government subsidized agricultural inputs such as fertilizer, seeds, agrochemicals | This reform area is to achieve allocation of 30% subsidized agro inputs to smallholder farmers living with disabilities and vulnerable women with the aim of increasing food production | A. Identify and collate data of persons living with disabilities and vulnerable women smallholder farmers across the 17LGAs | Persons living with disabilities, vulnerable women that are smallholder farmers. Target Objective: To promote access to sectoral public data for innovation and digital economy development | Plateau State Ministry of Agriculture and Rural Development |  |  | 6th May, 2022 | 31st December, 2023
|  |  | B. Verify the collated list and give potential beneficiaries means of identification | Target Objective: To keep up to date with the activities of the ecosystem and to inform the stakeholders | Plateau State Ministry of Agriculture and Rural Development | Plateau Ministry of Women Affairs, Disability Right Commission, LG Council, Ministry of Agriculture and Rural Development |  | 31st March, 2023 | 31st December, 2023
|  |  | C. Make budget estimate of items for the identified persons and profiled groups | Target Objective: To ensure that MSME obtain requisite support | Plateau State Ministry of Agriculture and Rural Development
|  |  | D. Set a distribution of subsidized items to the groups | Target Objective: Clear and practical guidelines for the distribution of subsidized items | Plateau State Ministry of Agriculture and Rural Development
|  |  | E. Monitor the distribution of subsidized items to the various categories | Target Objective: To provide implementable guidance for Information | Plateau State Ministry of Agriculture and Rural Development
|  |  | F. Prepare annual report on mainstreaming vulnerability and gender in the distribution of subsidized agroinputs | Target Objective: To establish trust in distribution processes | Plateau State Ministry of Agriculture and Rural Development
12 | Enactment and Launch of Plateau State Tourism Policy | To establish a direction and route map for development in the sector and thereby attract investments | A. Automation of processes | Potential Investors, Private Sector, MSMEs. Target Objective: To develop guidelines for sustainable management of processes | Plateau State Ministry of Tourism, Culture and Hospitality | Plateau State Tourism Corporation, Ministry of Tourism, Culture and Hospitality |  | 2nd February, 2023 | 31st December, 2023
|  |  | B. Registration, Classification and data caputuring of all Tourism and Cultural related Businesses in the State | Target Objective: To ensure compliance with all developmental regulatory instruments | Ministry of Tourism, Culture and Hospitality
|  |  | C. Develop policy implementation manual | Target Objective: To make all regulatory frameworks relevant for current realities | Ministry of Tourism, Culture and Hospitality
|  |  | D. Communicate the procedures to the personnel | Target Objective: To ensure personnel undestand and can carry out their responsibilities within the automated system | Ministry of Tourism, Culture and Hospitality
|  |  | E. Communicate the policy manual to the relevant stakeholders | Target Objective: Provide a platform where stakeholders can collaborate and exhibit their expertise, goods and services to drive investment | Ministry of Tourism, Culture and Hospitality
|  |  | F. Implement policy and track procedures | Target Objective: To build scalable capacity to take advantage of trade opportunities | Ministry of Tourism, Culture and Hospitality
|  |  | G. Monitor and Evaluate policy implementation quarterly | Target Objective: To improve the regulatory and governance mechanisms through implementation of unified governance structure | Ministry of Tourism, Culture and Hospitality
13 | Environmental Sector Reform | Stimulating economic activities through waste to wealth | A. Integrated Waste Management, Recycling and Energy Generation in Plateau State | Potential Investors, Private Sector, MSMEs. Target Objective: To develop guidelines for sustainable management of processes | Ministry of Environment | Ministry of Environment, Plateau Infrastructure and Regulatory Agency, Plateau Investment and Property Develoment Company (PIPC) Ltd, Ministry of Finance |  | 9th March, 2023 | 16th May, 2023
|  |  | B. Simplify the process and procedure for getting EIA by clarifying the steps and fees payable | Target Objective: Simplify the process and procedure to Seven steps | Ministry of Environment
14 | Gender mainstreaming and inclusive growth | To enhance opportunities for gender inclusion and reduce challenges for women in business | A. Implementation of the Plateau State Gender and Equal Opportunities Law, 2015 | MSMEs, PWDs, Private Sector. Target Objective: It will enable women and men to make decisions that impact more positively on their lives. | Ministry of Women Affairs | Office of the Head of Service, Ministry of Justice, Ministry of Women Affairs |  | 31st March, 2023 | 31st December, 2023
|  |  | B. Establishment of Gender and Equal Opportunities Commission | Target Objective: Facilitate the implemtation of the Law | Ministry of Women Affairs
|  |  | C. Designation, training and deployment of Gender Focal Persons in key MDAs (35) and all the 17 LGAs in the state | Target Objective: To train 2000 people in cluding people With Disabilities on Gender Mainstreaming | Ministry of Women Affairs
|  |  | D. Periodic engagements to address gender specific business constraints | Target Objective: Engage the stakeholders at the state and local government levels to support the goal of gender mainstreaming literacy level | Ministry of Women Affairs
|  |  | E. Monitor and Evaluate policy implementation periodically | Target Objective: To increase adoption of gender mainstreaming in the State; and improvement of the efficiency & effectiveness of government services | Ministry of Women Affairs
15 | Reforms in the Energy sector | This is to stimulate more investments into the energy sector | A. Develop State Policy and Strategy on Renewable Energy | Potential Investors, Private Sector, MSMEs. Target Objective: To develop guidelines for sustainable management of processes | Ministry of Water Resources and Energy | Office of the Governor, Ministry of Water Resources and Energy |  | 16th February, 2023 | 17th May, 2025
|  |  | B. Establish guidelines for Mini-Grid PPP development | Target Objective: To provide enabling framework for Mini-Grid PPP development to thrive maximally in the energy sector | Ministry of Water Resources and Energy
|  |  | C. Communicate policy manual to the key stakeholders | Target Objective: To establish trust with key stakeholders | Ministry of Water Resources and Energy
|  |  | D. Implement procedure | Target Objective: To facilitate the growth of smart-enabled technologies, resources and capabilities in energy critical sector | Ministry of Water Resources and Energy
|  |  | E. Monitor and Evaluate policy implementation periodically | Target Objective: To improve the regulatory and governance mechanisms through implementation of unified governance structure | Ministry of Water Resources and Energy
16 | Reform of the Critical Infrastructural Sector | This is to expand existing structures and develop new ones towards ensuring that such infrastructure like roads etc open up the state economic landscape. | A. Construction and completion of the Lalong Legacy projects initiated across the three senatorial districts of Plateau State. These projects comprise 4 modern hospitals, 3 vocational and technical schools etc | Private Sector, Individuals, Students, MSMEs. Target Objective: To improve the quality of life of people in the rural areas through imrpved health delivery and thereby enhance economic activties. In addition, improve vocational and technical skills development in schools and by extension support the growth of MSMEs in the State. | Ministry of Works, Minsitry of Housing, Ministry of Urban and Regional Planning, Ministry of Lands, Survey and Town Planning |  |  | 1st June, 2022 | 31st May, 2023
|  |  | B. Completion and commissioning of the British-American Overhead Bridge and Dualisation of Lamingo Junction Road | Target Objective: Prevent traffic congestion, and to ease the movement of goods and persons in to the Central Business District of Jos thereby lubricate economic activties resulting from reduced costs .
|  |  | C. Completion and commissioning of the State High Court Headquarters Complex | Target Objective: To enhance Judicial Services and by extension settlement of commerical disputes .
|  |  | D. Construction of Markets with modern facilities across the three senatorial districts to boost comerce and agricultural produce sector | Target Objectives: To revitalize the economy of the state with the vast opportunities it holds for individual commercial activities